## general_report
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Add to Requirements | Comments
Access | ITAMS-92 | Picklist issue | Mark A Hansen [X] | YenSheng Wang | Medium | To Do | Unresolved | 2016-08-03 09:27 | 2016-09-03 13:16 | Yes - Duplicate | having issue adding new "equipment Make". Simaliar to ITAM-73. browser / cache issue | Need more Info
Bug | ITAMS-300 | bulk upload issue | Jerry Liu | YenSheng Wang | Medium | To Do | Unresolved | 15/11/2016 10:31 | 20/12/2016 14:48 | Yes | Interminent. | Yes
Bug | ITAMS-181 | bulk update | Mark A Hansen [X] | Asim Hyder | Critical | To Do | Unresolved | 2016-09-08 10:46 | 28/09/2016 14:45 | Yes | releasing multiple assets back to inventory Update multiple status | Yes
Bug | ITAMS-178 | Bulk Upload | Unassigned | Erin Anne Adkins | High | To Do | Unresolved | 2016-03-08 05:58 | 2016-03-08 05:58 | Yes - Duplicate | Similar to Line Item 3 | 0
Bug | ITAMS-269 | Save issue | Mark A Hansen [X] | Asim Hyder | High | To Do | Unresolved | 15/09/2016 09:53 | 2016-11-11 10:45 | Yes |  | Yes
Bug | ITAMS-302 | Tried to add naila ghorbel as a technician and it didn't work | Hannah Yajing Wang | Bonnie McDonough | Medium | To Do | Unresolved | 2016-01-12 11:40 | 19/12/2016 12:57 | Yes | Issue with adding techs.May be a view issue, May be a browser issue | Yes
Bug | ITAMS-296 | Can Not Edit Description Field of a license | Mark A Hansen [X] | Kerry A Mckay | High | To Do | Unresolved | 2016-09-11 08:13 | 2016-11-11 10:44 | Yes |  | Yes |  | Yes
Bug | ITAMS-261 | Reassign function is missing from picklist section | Mark A Hansen [X] | YenSheng Wang | Medium | To Do | Unresolved | 14/09/2016 09:07 | 14/09/2016 09:44 | Yes | need to add it back up | Yes |  | Yes - Duplicate
Bug | ITAMS-259 | PickList Equipment type, Asset link not working | Unassigned | YenSheng Wang | Medium | To Do | Unresolved | 14/09/2016 09:03 | 14/09/2016 09:42 | Yes | could not add equipement model, may be tied to line item 9 | Yes |  | No
Bug | ITAMS-253 | Parent assets are not displayed when viewing child assets | Mark A Hansen [X] | Kerry A Mckay | High | In Review | Unresolved | 13/09/2016 11:49 | 13/09/2016 11:51 | Yes |  | Yes |  | Need more Info
Bug | ITAMS-251 | ITS and CAM users are allowed to see the create and modify asset buttons | Mark A Hansen [X] | Mark A Hansen [X] | High | To Do | Unresolved | 13/09/2016 08:55 | 13/09/2016 11:32 | Yes | Do not allow users to edit. Check with ITS if this is needed | Need more Info |  | Resolved
Bug | ITAMS-248 | Unable to Return 256499 to Inventory. | Unassigned | Erin Anne Adkins | High | To Do | Unresolved | 13/09/2016 07:47 | 13/09/2016 09:28 | Yes - Duplicate | This is "save" issue. Simaliar with ITAM-269. see detail --- Was Returning 256499 to Inventory, made changes to Responsible Parties*; Location*; Unlink Assets*; Unlink Software*; Clicked Update Staus button and Red Circle with line through it appeared and no change was made. | Need more Info
Bug | ITAMS-243 | Force to enter Status Detail | Unassigned | Edward C Pfleger | Medium | To Do | Unresolved | 2016-12-09 13:28 | 2016-12-09 13:28 | Resolved | fixed | Need more Info | .
Bug | ITAMS-213 | Cannot add software licenses to an asset. | Mark A Hansen [X] | Gerald Rickard | High | In Progress | Unresolved | 2016-08-09 13:40 | 2016-09-09 09:23 | Yes |  | Yes
Bug | ITAMS-189 | Unable to create assets back to back | Unassigned | Erin Anne Adkins | High | To Do | Unresolved | 25/08/2016 07:56 | 25/08/2016 07:56 | Yes |  | Yes
Bug | ITAMS-175 | Cannot save when changing role in permissions | Unassigned | Erin Anne Adkins | High | To Do | Unresolved | 2016-02-08 14:21 | 2016-02-08 14:21 | Yes |  | Yes
Bug | ITAMS-170 | Unable to edit users | Unassigned | Erin Anne Adkins | High | To Do | Unresolved | 2016-01-08 07:45 | 2016-01-08 07:45 | Yes |  | Yes
Bug | ITAMS-164 | Second linked asset does not show linked assets | Mark A Hansen [X] | Robyn Pass | High | Internal Testing | Unresolved | 29/07/2016 16:01 | 13/09/2016 11:51 | Yes |  | Yes
Bug see 109 | ITAMS-163 | When adding an asset, location field issue | Mark A Hansen [X] | Robyn Pass | High | In Review | Unresolved | 29/07/2016 15:45 | 2016-10-08 12:50 | Yes | Under Assets tab, when adding asset, the drop down for location only has a limited amount of locations. If you try to type in a new location, the field lags until the page won't load until you refresh. | Need more Info
Bug | ITAMS-144 | Encryption Date not accurate | Mark A Hansen [X] | Asim Hyder | Medium | To Do | Unresolved | 2016-11-07 10:08 | 2016-11-07 13:33 | Resolved | fixed | 0
Bug see 109 | ITAMS-115 | Linking asset does no change any location Information | YenSheng Wang | Kerry A Mckay | High | To Do | Unresolved | 2016-03-06 15:30 | 2016-03-06 15:30 | Yes | refer to line 21 | Yes
Bug | ITAMS-111 | Unable to enter a letter in the lease schedule field | YenSheng Wang | YenSheng Wang | Low | To Do | Unresolved | 23/05/2016 09:21 | 23/05/2016 09:21 | Yes | Fixed | Yes
Bug | ITAMS-110 | re-assign assets gives error | Mark A Hansen [X] | Cung M Ha | High | To Do | Unresolved | 2016-09-05 14:45 | 2016-09-05 15:04 | Yes | reassign asset | Yes
Bug | ITAMS-104 | Failed to Load Context of Certain Users | Mark A Hansen [X] | Kerry A Mckay | High | In Review | Unresolved | 2016-06-04 08:54 | 19/04/2016 11:22 | Yes | can't see dashboard for their context | Yes
Bug see 110 | ITAMS-93 | Return to Inventory needs an additional field to select that allows changing the "General Information - Department" field. When inventory is returned to idle then you have to go into the asset\General Information and manually make that modification. This is a significant work flow issue for the GADM support group and a major issue for hardware refresh cycles. | YenSheng Wang | Kerry A Mckay |  | To Do | Unresolved | 2016-11-03 10:45 | 13/07/2016 08:23 | Yes | Return to Inventory needs an additional fields to select that allows changing the "General Information - Department" field. When inventory is returned to idle then you have to go into the asset\General Information and manually make that modification. This is a significant work flow issue for the GADM support group and a major issue for hardware refresh cycles. | Need more Info
Bug | ITAMS-88 | When selecting Return To Inventory from Actions and you make all the changes including Owner Information which includes Department as a field it does not also change the Department field under General Information. | YenSheng Wang | YenSheng Wang |  | To Do | Unresolved | 2016-04-02 13:02 | 2016-04-02 13:02 | Yes - Duplicate | Same with ITAM-93. row 26 | Need more Info
Bug | ITAMS-84 | Ignore previous bug report, it looks like it just ... | YenSheng Wang | Bonnie McDonough |  | To Do | Unresolved | 30/11/2015 09:04 | 13/07/2016 08:23 | Resolved | fixed | Need more Info
Bug | ITAMS-83 | Changing asset from ACTIVE to Personal Buyout does... | YenSheng Wang | YenSheng Wang |  | To Do | Unresolved | 30/11/2015 09:03 | 27/05/2016 10:32 | Resolved | same with ITAM-84, row 28 FIXED | Need more Info
Bug | ITAMS-80 | When you link an asset from a (UCT, OCB or SOD) overhead account to a computer, the owner information does not update to the customer who the PC is assigned to. The owner information still reads (UCT, OCB or SOD) overhead. We have to manually change the owner information on the linked asset | YenSheng Wang | YenSheng Wang |  | To Do | Unresolved | 27/10/2015 10:46 | 27/05/2016 10:37 | Yes - Duplicate | Reqeust. simaliar with ITAM-93. when link asset. The child asset general info need to be update automatically (owner, location, department…) as same as the parent asset. | Need more Info
Bug | ITAMS-79 | Can't add a service account to Permissions because... | YenSheng Wang | YenSheng Wang/ Kerry |  | To Do | Unresolved | 27/10/2015 09:05 | 27/10/2015 09:05 | Yes | Can't add a service account to Permissions because there is no e-mail associated with it. Need to be able to add a user account to Permissions by user name or UID instead of having to use e-mail. We use contractors for projects and they will do data entry but now I can't add the service accounts we create because there is no e-mail address associated with it. It's not LDAP is AD only. | Need more Info
Bug | ITAMS-73 | Added Campus for Netops from Chrome. but not showing on both Chrome or IE | YenSheng Wang | YenSheng Wang | Lowest | To Do | Unresolved | 30/09/2015 14:25 | 19/10/2015 11:39 | Yes | Browser issues (IE/Chrome) | Yes
Bug | ITAMS-40 | CAM Tag: 192194 was recently created without a Sys... | YenSheng Wang | YenSheng Wang | Lowest | To Do | Unresolved | 24/08/2015 09:48 | 19/10/2015 11:41 | Resolved | fixed | Need more Info
Bug | ITAMS-4 | 258362 was Returned to Inventory via the Actions Drop Down and 998942 was a Linked Asset. Viewing 998942 after the Return to Inventory the General Information: Department: did not change from Telecommunications to Overhead. Location Information: did not change from OCB 1.230-3 to OCB 2.130. Owner Information; updated correctly. | YenSheng Wang | YenSheng Wang | Lowest | To Do | Unresolved | 2015-11-08 15:16 | 19/10/2015 11:45 | Yes - Duplicate | same as ITAM-93. riw 26 | Need more Info
Change | ITAMS-281 | Cannot attach file 20150811 ITAMS 998942 Return to Inventory.docx: JIRA could not attach the file as there was a missing token. Please try attaching the file again. | Mark A Hansen [X] | Mark A Hansen [X] | High | To Do | Unresolved | 23/09/2016 10:01 | 23/09/2016 10:05 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-280 | Data Integrity: 373 duplicated responsible parties | Jerry Liu | Mark A Hansen [X] | Medium | To Do | Unresolved | 23/09/2016 09:57 | 23/09/2016 10:01 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-279 | Data Integrity: 1013 duplicated locations | Jerry Liu | Mark A Hansen [X] | Medium | To Do | Unresolved | 23/09/2016 09:55 | 27/10/2016 13:52 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-278 | Data Integrity: 267 duplicate buildings | Jerry Liu | Mark A Hansen [X] | Medium | To Do | Unresolved | 23/09/2016 09:53 | 27/10/2016 13:52 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-277 | Data Integrity: 636 duplicate equipment models | Jerry Liu | Mark A Hansen [X] | Medium | To Do | Unresolved | 23/09/2016 09:48 | 23/09/2016 10:03 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-276 | Data Integrity: 55 duplicate equipment makes | Jerry Liu | Mark A Hansen [X] | Medium | To Do | Unresolved | 23/09/2016 09:47 | 23/09/2016 10:03 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-275 | Data Integrity: 9 duplicate equipment types | Jerry Liu | Mark A Hansen [X] | Medium | To Do | Unresolved | 23/09/2016 09:46 | 23/09/2016 10:02 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-274 | Data Integrity: 7 duplicate encryption types | Jerry Liu | Mark A Hansen [X] | Medium | To Do | Unresolved | 23/09/2016 09:43 | 23/09/2016 10:02 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-273 | Data Integrity: 14 duplicate operating systems | Jerry Liu | Mark A Hansen [X] | Medium | To Do | Unresolved | 23/09/2016 09:42 | 23/09/2016 10:02 | Yes | Combine and consolidate duplicates Standardize lookup tables Limit who can add values (Models …) Add a 3rd role/ Admin roles | Yes
Change | ITAMS-241 | Bulk update | Unassigned | YenSheng Wang | Medium | To Do | Unresolved | 2016-12-09 10:24 | 2016-12-09 10:24 | Yes - Duplicate | Duplicate- Line item 4 | 0
Change | ITAMS-233 | Remove Location Auto add | Unassigned | Erin Anne Adkins | Low | To Do | Unresolved | 2016-09-09 15:30 | 2016-09-09 15:56 | Resolved | Fixed | 0
Fault | ITAMS-157 | ITAMS 1.2 Upgrade failed | Mark A Hansen [X] | Mark A Hansen [X] | Critical | To Do | Unresolved | 26/07/2016 10:16 | 26/07/2016 10:16 | No | Not applicable | 0
Improvement | ITAMS-287 | Redesign Location Search | Mark A Hansen [X] | Mark A Hansen [X] | Highest | To Do | Unresolved | 27/09/2016 12:10 | 27/09/2016 12:11 | No | Not applicable | 0
Improvement | ITAMS-245 | Date/Time on CAM Info | Unassigned | Edward C Pfleger | Low | To Do | Unresolved | 2016-12-09 15:07 | 14/09/2016 09:52 | Yes | Can we get the date/time on the CAM info set to the American standard? | Need more Info
Improvement | ITAMS-205 | Editing Owner Information | Mark A Hansen [X] | Michael Anthony Vasquez | Low | In Review | Unresolved | 2016-08-09 09:45 | 2016-09-09 17:18 | Yes | a lot of issues | Yes
Improvement | ITAMS-154 | When entering text into one of the dropdown searches, instead of searching alphabetically for any item with that particular string, it should contextually start searching with the string entered. (i.e. If a user were to enter "DE", searching for Dell, it should start searching for results that start with DE not a result that has "DE" somewhere in the middle of it.) | Mark A Hansen [X] | Mikal D Hensarling | Medium | To Do | Unresolved | 15/07/2016 10:38 | 15/07/2016 10:38 | Yes | Summary updated | Need more Info
Improvement | ITAMS-153 | Allow dropdown lists to create new entries. | Mark A Hansen [X] | Mikal D Hensarling | Medium | To Do | Unresolved | 15/07/2016 10:37 | 15/07/2016 10:37 | No | Link to Data integrity issue | No
Improvement | ITAMS-145 | Pop Up message for associated items when making a change to an Asset | Mark A Hansen [X] | YenSheng Wang | Medium | To Do | Unresolved | 2016-11-07 12:25 | 2016-12-07 07:54 | Yes | give a prompt | Yes
Improvement | ITAMS-114 | Improve workflow surrounding linked assets | Mark A Hansen [X] | Mark A Hansen [X] | Highest | To Do | Unresolved | 27/05/2016 10:43 | 27/05/2016 10:43 | Yes - Duplicate | Same as ITAM-93. row 26 | Need more Info
Improvement | ITAMS-77 | Show a warning when duplicate pieces of information are entered | Mark A Hansen [X] | YenSheng Wang | Lowest | In Review | Unresolved | 2015-07-10 11:02 | 13/04/2016 15:45 | Yes |  | Yes
Improvement | ITAMS-76 | Display a record of software changes | Mark A Hansen [X] | Kerry A Mckay | Medium | To Do | Unresolved | 2015-07-10 10:26 | 2015-07-10 10:26 | Yes | Revise change log | Yes
Improvement | ITAMS-75 | Add timestamp on document display page | Mark A Hansen [X] | Mark A Hansen [X] | Lowest | In Progress | Unresolved | 2015-01-10 10:15 | 14/03/2016 11:15 | Resolved | May have been fixed in the previous version | Need more Info
Improvement | ITAMS-38 | Allow technicians to delete files attached to assets with approval | Mark A Hansen [X] | Edward C Pfleger | Medium | To Do | Unresolved | 19/08/2015 13:59 | 19/10/2015 14:08 | Yes | Tied to line 44 | Yes
Improvement | ITAMS-35 | Allow setting of context default for pick lists | Mark A Hansen [X] | Bonnie McDonough | High | In Progress | Unresolved | 18/08/2015 14:55 | 19/10/2015 14:07 | No | need to have school specific defaults | No
Improvement | ITAMS-34 | Sortable Columns for Asset List | Mark A Hansen [X] | Bonnie McDonough | Low | To Do | Unresolved | 18/08/2015 14:55 | 25/08/2015 14:21 | Yes |  | Yes
Improvement | ITAMS-33 | Add Re-Assign feature to Departments | YenSheng Wang | Bonnie McDonough | Lowest | To Do | Unresolved | 18/08/2015 14:54 | 2015-05-11 11:14 | Yes | Related to a previous item | Yes
Improvement | ITAMS-27 | Add pick list for "License Form" to make it options uniform. Under editing license. | YenSheng Wang | YenSheng Wang | Lowest | To Do | Unresolved | 18/08/2015 14:52 | 19/10/2015 11:43 | Yes | have a uniformed way of entering licenses! Kerry | Need more Info
Improvement | ITAMS-26 | Synchronize asset owner and location when linking assets | YenSheng Wang | YenSheng Wang | Lowest | To Do | Unresolved | 18/08/2015 14:52 | 19/10/2015 11:43 | Yes | Related to a previous item | Yes
Improvement | ITAMS-21 | [Heat Ticket #01229917] Mobile Version | Mark A Hansen [X] | YenSheng Wang | Medium | To Do | Unresolved | 18/08/2015 14:50 | 18/08/2015 14:50 | No | Wish list: tech being able to use mobile phone to scan asset. Do inventory on premise. | Need more Info
Improvement | ITAMS-19 | [Heat Ticket #01229731] Allow administrators to view deleted software | YenSheng Wang | Kerry A Mckay | Lowest | To Do | Unresolved | 18/08/2015 14:49 | 19/10/2015 11:44 | Yes | Admin roles task - If a software is accidentially deleted there is no way to research or find it for restoration. It also gets purged from the database so it can't be cross referenced in the database reporting tool (DBxtra) | Yes
Improvement | ITAMS-18 | Implement Web API changes for IsDefault functions | Mark A Hansen [X] | Mark A Hansen [X] | High | To Do | Unresolved | 18/08/2015 14:49 | 19/10/2015 14:07 | No | remove | No
Improvement | ITAMS-17 | Implement DB changes for IsDefault functions | Mark A Hansen [X] | Mark A Hansen [X] | High | To Do | Unresolved | 18/08/2015 14:48 | 19/10/2015 14:07 | No | remove | No
Improvement | ITAMS-16 | Implement UI changes for IsDefault functions | Mark A Hansen [X] | Mark A Hansen [X] | High | To Do | Unresolved | 18/08/2015 14:48 | 19/10/2015 14:08 | No | remove | No
Improvement | ITAMS-15 | Implement pre-selected context defaults for UI picklists | Mark A Hansen [X] | Kerry A Mckay | High | To Do | Unresolved | 18/08/2015 14:48 | 19/10/2015 14:08 | Yes | The defaults for campus, building, and location. Extend this functionality to other pick list items. For each pick list collection, allow context administrators to select a default value. | Need more Info
Improvement see 102 102A&102B | ITAMS-14 | Provide Additional Search filters on dashboard | YenSheng Wang | Kerry A Mckay | Lowest | To Do | Unresolved | 18/08/2015 14:48 | 19/10/2015 11:44 | Yes | better sort functionalities on the dashboards (Eg:60) | Yes
Improvement see 105 | ITAMS-13 | Heat Ticket [01259886]: Restrict Bulk Upload Equipment models to predefined values | YenSheng Wang | Kerry A Mckay | Lowest | In Review | Unresolved | 18/08/2015 14:47 | 22/06/2016 10:26 | Yes | Admin roles task and Bulk upload | Yes
New Feature | ITAMS-294 | A field indicating 100% state funded employee and/or teaching faculty | Unassigned | Edward C Pfleger | Medium | To Do | Unresolved | 2016-03-11 07:46 | 15/11/2016 09:46 | No | In place. SPH Only | No
New Feature | ITAMS-74 | Able to select the Department under Owner information. instead of maintain department for GAL or Responsible parties on picklist | YenSheng Wang | YenSheng Wang | Lowest | To Do | Unresolved | 30/09/2015 14:26 | 19/10/2015 11:38 | Yes | if the responsible parties is not maintain inside picklist. It will auto create when input into owner area. But since the department is mandatory when create responsible parties. We need a department drop down to choose from. Instead go into picklist and create a new one. | Need more Info
New Feature | ITAMS-71 | Technicians should be able to remove documents from assets. | Mark A Hansen [X] | YenSheng Wang | Medium | To Do | Unresolved | 28/09/2015 10:04 | 19/10/2015 14:09 | Yes | Define a premission matrix, James : I am the only person can remove document from MS side | Need more Info
New Feature | ITAMS-57 | Add new Column for PO number. under Lease info area. | Mark A Hansen [X] | YenSheng Wang | Medium | To Do | Unresolved | 2015-10-09 07:31 | 19/10/2015 14:09 | Yes |  | Yes
New Feature | ITAMS-30 | Technicians should be able to create software | Mark A Hansen [X] | YenSheng Wang | Lowest | In Progress | Unresolved | 18/08/2015 14:53 | 14/03/2016 11:18 | Yes - Duplicate | Define a premission matrix | Need more Info
New Feature | ITAMS-28 | Directory listing for office location and contact information shown for User / Owner display | YenSheng Wang | YenSheng Wang | Lowest | To Do | Unresolved | 18/08/2015 14:52 | 19/10/2015 11:43 | Yes | add and edit exceptions | Need more Info
New Feature | ITAMS-25 | [Heat Ticket: #01206899] Allow filtering of available unlinked assets by status | Mark A Hansen [X] | YenSheng Wang | Medium | To Do | Unresolved | 18/08/2015 14:51 | 18/08/2015 14:51 | Yes | "Available Unlinked Assets" is appearing to pull from "all" categories of assets. May need "equipment type" drop down to choose from. Need discussion. | Need more Info
New Feature | ITAMS-24 | No required message or error is displayed when creating a Responsible Party with no GAL Contact | YenSheng Wang | YenSheng Wang | Lowest | To Do | Unresolved | 18/08/2015 14:51 | 19/10/2015 11:43 | Yes | still no required message or errors and I can't create any responsible parties now. with or without GAL/department | Need more Info
New Feature | ITAMS-23 | [Heat Ticket: #01229938] Implement an interface for bulk changes | YenSheng Wang | Bonnie McDonough | Highest | In Progress | Unresolved | 18/08/2015 14:51 | 26/10/2016 14:02 | Yes - Duplicate | Duplicate - Line Item 4 | 0
New Feature | ITAMS-20 | [Heat Ticket #01229916] Integrate with CSI | Mark A Hansen [X] | Kerry A Mckay | Medium | To Do | Unresolved | 18/08/2015 14:49 | 18/08/2015 14:49 | Yes | Wish list !!!!!!!!! | 0
Sub-task | ITAMS-263 | ITAMS-262 Users are unable to see the entire location | Mark A Hansen [X] | YenSheng Wang | Medium | To Do | Unresolved | 14/09/2016 09:46 | 14/09/2016 09:46 | Resolved | fixed | Need more Info
Sub-task | ITAMS-257 | ITAMS-262 There is nothing to choose from in the Campus field when adding a Location | Unassigned | Erin Anne Adkins | High | To Do | Unresolved | 14/09/2016 08:05 | 27/09/2016 12:14 | Resolved | fixed | Need more Info
Sub-task | ITAMS-256 | ITAMS-262 Unable to setup location for SON assets | Mark A Hansen [X] | Marceli Palak | High | To Do | Unresolved | 13/09/2016 14:26 | 14/09/2016 09:51 | Resolved | fixed | 0
Sub-task | ITAMS-255 | ITAMS-262 Unable to enter new locations using asset location field | Mark A Hansen [X] | Alice Mireles | High | To Do | Unresolved | 13/09/2016 13:57 | 14/09/2016 09:50 | Resolved | fixed | 0
Sub-task | ITAMS-254 | ITAMS-262 Order Create Location Pick-list fields | Mark A Hansen [X] | Edward C Pfleger | Low | In Review | Unresolved | 13/09/2016 12:16 | 14/09/2016 15:00 | Resolved | fixed | Need more Info
Sub-task | ITAMS-240 | ITAMS-262 Location Tab/Bar | Mark A Hansen [X] | Raymond Sterling Skillern | High | To Do | Unresolved | 2016-12-09 09:33 | 27/09/2016 12:16 | Resolved | fixed | Need more Info
Sub-task | ITAMS-238 | ITAMS-262 Location search function does not return results reliably | Mark A Hansen [X] | James Oliver Whitehead | High | To Do | Unresolved | 2016-12-09 09:17 | 27/09/2016 12:16 | Yes |  | Yes
Sub-task | ITAMS-218 | ITAMS-262 under the location | Erin Anne Adkins | Asim Hyder | Low | To Do | Unresolved | 2016-09-09 09:00 | 27/09/2016 12:16 | Resolved | fixed | Need more Info
Sub-task | ITAMS-161 | ITAMS-117 Software - add new software. add new software. after input all info. either press save or save and add another... it pop up message show " software added" but the browser freeze . need to shut down and reopen the browser again . The software i added not show on the Software area. | Mark A Hansen [X] | YenSheng Wang | Highest | In Review | Unresolved | 28/07/2016 09:20 | 2016-11-08 11:24 | Resolved | may be tied to SW Licensing bug. This is Staging server bug | Need more Info
Sub-task | ITAMS-160 | ITAMS-117 Software - license used. When check Software - Used Count. and click on the link that show how many computers use the license. it suppose to show the computer. but it stuck and keep rolling/loading....you have to shut down the browser to start over. | Mark A Hansen [X] | YenSheng Wang | High | In Review | Unresolved | 28/07/2016 09:13 | 2016-10-08 14:18 | Resolved | fixed, Staging server bug | Need more Info
Sub-task | ITAMS-152 | ITAMS-117 Test #2 When editing an asset… 1. There aren’t a... | Mark A Hansen [X] | Mikal D Hensarling |  | In Review | Unresolved | 13/07/2016 15:36 | 15/07/2016 11:53 | Resolved | fixed, Staging server bug | Need more Info
Sub-task | ITAMS-151 | ITAMS-117 IE Bulk Upload Layout is broken | Mark A Hansen [X] | Edward C Pfleger |  | In Review | Unresolved | 13/07/2016 14:11 | 19/07/2016 13:35 | Yes - Duplicate | duplicate - Line Item 3 | 0
Sub-task | ITAMS-150 | ITAMS-117 Test #1 1. When adding a new asset, dropdown li... | Mark A Hansen [X] | Edward C Pfleger |  | In Review | Unresolved | 13/07/2016 15:10 | 15/07/2016 10:38 | Resolved | fixed, Staging server bug | Need more Info
Sub-task | ITAMS-149 | ITAMS-117 The interface hangs when adding an asset | Mark A Hansen [X] | Mark A Hansen [X] | Highest | In Review | Unresolved | 14/07/2016 12:16 | 15/07/2016 09:38 | Yes | Still hangs | Yes
Sub-task | ITAMS-148 | ITAMS-117 The close X in the top right of popup windows does not work | Mark A Hansen [X] | Mikal D Hensarling | Low | In Review | Unresolved | 13/07/2016 10:17 | 15/07/2016 09:59 | Yes |  | Yes
Sub-task | ITAMS-143 | ITAMS-117 Return to Inventory Button is missing | Mark A Hansen [X] | Robyn Pass | High | In Review | Unresolved | 2016-08-07 14:51 | 18/07/2016 09:41 | Resolved | Fixed | No
Sub-task | ITAMS-141 | ITAMS-117 There is no licensing information available when c... | Mark A Hansen [X] | Stephen R Legrow |  | To Do | Unresolved | 2016-05-07 15:48 | 13/07/2016 08:22 | No | requirement not being recalled, to be added later if needed. Closing Line item | Need more Info
Sub-task | ITAMS-137 | ITAMS-117 Staging site : permissions link not working. | Mark A Hansen [X] | YenSheng Wang |  | In Progress | Unresolved | 2016-06-07 09:16 | 28/07/2016 09:03 | Resolved | fixed | No
Sub-task | ITAMS-132 | ITAMS-117 Picklist - Responsible Party | Mark A Hansen [X] | YenSheng Wang | Medium | In Progress | Unresolved | 27/06/2016 14:14 | 28/07/2016 08:58 | Resolved | fixed | No
Sub-task see 109 | ITAMS-113 | ITAMS-114 Apply parent asset updates to child assets | Mark A Hansen [X] | Kerry A Mckay | Highest | To Do | Unresolved | 27/05/2016 10:39 | 27/05/2016 10:44 | Yes | Related to a previous item | Yes
Sub-task see 109 | ITAMS-112 | ITAMS-114 Linking assets should update child assets with parent information | Mark A Hansen [X] | Kerry A Mckay | Highest | To Do | Unresolved | 27/05/2016 10:37 | 27/05/2016 10:44 | Yes | Related to a previous item | Yes
Search - Software Assignment Search
Picklist Permissions
Change Log
Bulk Change
Comments
Back Button
Primary Object
Assign Equipment
Return Equipment - Reassign Equipment
Reassign Equipment
Reporting Tool - DBXtra
Creating New Software \ Caching

## Need More Info
Add to Requirements | Need more Info
Row Labels | Count of Add to Requirements
YenSheng Wang | 18
Edward C Pfleger | 4
Mark A Hansen [X] | 3
Mikal D Hensarling | 2
Erin Anne Adkins | 2
Kerry A Mckay | 2
Bonnie McDonough | 1
Robyn Pass | 1
Asim Hyder | 1
Raymond Sterling Skillern | 1
Grand Total | 35