UTHealth Construction Schedule Review Checklist

| Project Name: |  |  |
| --- | --- | --- |
| Schedule Name: |  | UTHealth PM Response: | Accepted Rejected |
| Data Date: |  | Reason For Resubmittal: |  |
| Review Date: |  |  |  |

YES NO

- Schedule has been provided in Microsoft Project

- Schedule is organized by an appropriate Work Breakdown Structure (WBS) that aligns with the construction documents and pay application Schedule of Values (SOV)

- Schedule includes 15 days for submittal review

- Schedule includes correct Notice To Proceed (NTP) Date, Substantial Completion Date, and Final Completion Date in accordance with NTP

- Sequence and duration of activities is appropriate for the Project

- Schedule includes 2 weeks for TAB

- Schedule includes the minimum 10% Total Float

- Number of procurement activities is appropriate and are linked to their associated fabrication and delivery activities

- Number of contractor fabrication and delivery activities is appropriate and are linked to their associated work activities

- Number, type, and of detail of Contractor and Owner Commissioning activities is appropriate

- Number of Owner review and inspection activities is appropriate and follows the appropriate contractor inspections (wall and ceiling coverup and final punch at a minimum)

- All life safety, security, accessibility, HVAC, FCMS/BAS commissioning activities are shown to be completed prior to Substantial Completion

- All Owner training activities are shown to be completed prior to Substantial Completion

- Schedule has only one activity without a predecessor (typically NTP), and one activity without a successor (typically, Final Completion or Operation Occupancy)

- Schedule identifies the longest/critical path which includes both Substantial Completion and Final Completion

- Individual activities do not include excessive float